## Gantt - timeline for submission
TOOL E: EXAMPLE Funding Proposal Preparation Gantt/Timeline
Timeline for Application Development & Submission
NOFA #
Date |  | Th | Fr | Sa | Su | Mo | Tu | Wed | Th | Fr | Sa | Su | Mo | Tu | Wed | Th | Fr | Sa | Su | Mo | Tu | Wed | Th | Fr | Sa | Su | Mo | Tu | Wed | Th | Fr | Sa | Su | Mo | Tu
| ASSIGNED | 4/1 | 4/2 | 4/3 | 4/4 | 4/5 | 4/6 | 4/7 | 4/8 | 4/9 | 4/10 | 4/11 | 4/12 | 4/13 | 4/14 | 4/15 | 4/16 | 4/17 | 4/18 | 4/19 | 4/20 | 4/21 | 4/22 | 4/23 | 4/24 | 4/25 | 4/26 | 4/27 | 4/28 | 4/29 | 4/30 | 5/1 | 5/2 | 5/3 | 5/4
Planning & Discovery | bar: Sa
Read NOFA | bar: Th; Sa
Draft Gantt (timeline) | bar: Th to Su; Sa
Draft checklists | bar: Th to Su; Sa
Meet as team to discuss and agree upon scope/timeline/working title+ | bar: Mo; Wed; Sa
Set meeting schedule & ID POCs & SME contacts | bar: Mo; Sa
Identify shared document platform/give access to Contractor | bar: Mo; Sa
Set up project file structure | bar: Mo to Su; Sa
Update Gantt & checklists | bar: Mo to Sa
Conduct pre-application call | bar: Wed; Sa
Research | bar: Sa
Confirm/Request DUNS, SAM, HUD grant registration+ | bar: Mo to Th; Sa
Identify/download needed documents from Grants.gov application portal | bar: Mo to Th; Sa
Pull and convey needed documentation to/access | bar: Mo to Su; Sa
Review organizational docs/prior grants/qualifications, etc. | bar: Mo to Mo; Sa
Organization requests letters of support/resumes from appropriate staff | bar: Mo to Mo; Sa
Converse with partner organizations | bar: Fr to Su; Sa
Conduct initial literature review & begin "works cited" Appendix | bar: Mo to Su; Sa
Writing & Reviewing | bar: Sa
Draft abstract, narrative statement, Appendix A | bar: Wed to Sa
Collect & complete federal forms & further draft appendices | bar: Fr to Sa
Draft budgets/totals & narrative budget justification | bar: Sa to Su
Review draft narrative, budget, justification, appendices and forms | bar: Th to Th
CEO review (or designee) | bar: Sa; Mo to Wed
Submission | bar: Sa; Mo to Wed
Standard forms, certifications uploaded to portal | bar: Sa to Sa
Letters of support & other supplemental materials uploaded | bar: Th to Fr
Abstract, narrative, Appendices and budget justification uploaded | bar: Sa; Sa to Su
Budget sheets uploaded | bar: Sa; Sa to Su
Final review of aggregrate online application | bar: Sa; Th to Mo
FINAL submission | bar: Sa; Sa to Mo
LEGEND
= Ideal timeline to complete this item
= Self review and wrap this item up
|  |  | = Absolute deadline |  |  |  |  | = danger!
= Item completed
= In progress
= Not yet started

## App - existing documentation
Sample Check List - Existing Documentation
Client Name
Date
# | Existing Documentation Needed | Doc/Info | Recieved | Date Re'd
1 | DUNS # | Info
2 | SAM registration #/proof | info
3 | 501(c)3 letter | Doc
4 | Audited Report of Financial Statements | Doc
7 | IDC Agreement (federal) - if applicable | Doc
8 | HUD registration/PCOA login | info
9 | FY21 Organizational Budget | Doc
10 | Key personnel resumes | Doc
11 | Proof of Insurance/Indemnity | Doc
12 | Organizational Chart | Doc
13 | MOU's with partner organizations, government, LE, legal | Doc

## App - new documents
Sample Check List - New Documentation
Date
# | New/Compiled Documentation Needed |  | Doc/Info | Received? | Date Rc'd | Status
1 | Federal (Standard) Forms
2 | Requested letters/certifications
3 | Org documentation
Organizational assurances
IRS determination letter
Audit a/o management letter
Organizational FY21 budget
Last year's 990
Proof of insurance/required indemnity
4 | Narrative
Abstract
Narrative
Appendices
Revised key personnel resumes
Appendix A chart
References/Works Cited
5 | Budget
Worksheets
Narrative justifcation